# MGIA Grant Program

# Scope of Work Development Workbook

FY2027 Grant Period

Published January 2026

Contents

How to use this Workbook	2

Step-by-step process for developing your SOW	3

Defining Goals and Objectives	3

Describing Tasks	3

Describing Deliverables	4

Additional requirements for equipment purchases	4

Quick SOW checklist	4

Application SOW Template	4

# How to use this Workbook

A Scope of Work (SOW) template is included in this document and are pre-formatted to help you organize goals, objectives, tasks, and deliverables correctly. Applicants should complete their SOW using the template and once finalized, copy the completed SOW into the designated Scope of Work section of the application document. The multilevel list format used in the examples and template is the required structure for all SOWs.

Applicants are encouraged to reach out to the MSDI Theme Leads for technical questions, guidance, and examples for completing the SOW.

## Step-by-step process for developing your Scope of Work

- Draft your goals and measurable objectives in the template.

* If necessary, contact the appropriate  MSDI Theme Lead for guidance.

- Add tasks under each objective in chronological order, ensuring each task includes a clear description and a completion date.

- Add separate tasks for each equipment purchase, including justification for how each purchase supports your goals and objectives.

- List all deliverables and verify that each major task leads to at least one deliverable.

- Review the completed SOW using the checklist below, then copy it into the Scope of Work section of the application document.

## Defining Goals and Objectives

Goals and objectives explain what the project intends to achieve and how success will be measured.

- Goals are broad, high-level statements that describe the overall purpose or long-term impact of the project.

- Objectives are specific, measurable outcomes that support each goal and state what will be achieved and by when.

Each project should have one or more clearly stated goals, and every goal must have at least one measurable objective. Each objective should describe a concrete outcome and the timeframe in which that outcome will be achieved.

A helpful pattern for writing objectives is:

- “By [date], [who] will [do what] to produce [specific result].”

For example: “By June 30, 2026, the County GIS Office will complete address point corrections in all incorporated areas to meet NG9-1-1 accuracy requirements.”

## Describing Tasks

Tasks explain what work will be done to accomplish each objective.

- List tasks in chronological order under the objective they support.

- Describe each task in enough detail to show that the work is realistic, clearly understood, and directly tied to the objective.

- Make clear what specific result or product will show that the task is complete.

When defining tasks, follow these requirements:

- Every task must include a completion date.

- All work must be completed within the two-year grant period, although projects may finish sooner.

- All equipment purchases must be listed as separate tasks.

## Describing Deliverables

Deliverables are the tangible products and outputs created by the project.

Provide a complete list of all project deliverables, making sure they align directly with the tasks described under each goal and objective. Examples of deliverables include:

- Data sets or databases

- Scripts or code

- Maps or map services

- Training materials and documentation

- Photographs or videos

- Written workflows or standard operating procedures

For every major goal, applicants should be able to point to at least one deliverable that demonstrates the task has been completed. The SOW should make it clear how each deliverable results from specific tasks and supports the project’s goals and objectives.

## Additional requirements for equipment purchases

Each equipment purchase must:

- Be listed as its own task in the SOW.

- Be clearly described (what is being purchased and how it will be used).

- Include specific justification showing how the purchase will help achieve the project’s goals and objectives.

Example task description:
“Purchase GPS receiver to support field data collection for new address points; this equipment will enable collection of accurate locations needed to meet NG9-1-1 and MSDI standards.”

Note: All equipment purchases must comply with section 90-1-411(1), MCA, which limits use of funds to purposes such as purchasing technology that assists in collecting, maintaining, or disseminating geographic information systems, geospatial information, or geospatial technologies.

## Quick SOW checklist

Before submitting, confirm that your SOW includes:

- At least one broad project goal.

- At least one measurable objective for each goal.

- Chronological tasks under each objective, each with a completion date.

- Separate tasks for each equipment purchase, with clear justification.

- A clear list of deliverables that match the tasks.

# Application SOW Template

[Continue with additional goals, objectives, tasks, and completion dates as needed]