## Improvement Plan
MSDI Data Improvement Plan
Theme: Elevation
Core products: Point Cloud, Digital Elevation Model, Digital Surface Model, Intensity, Canopy Height Model, Hillshade. Related products: contours, building footprints
Summary five year goals: Narrative - Process (and plan) in place to generate a complete statewide coverage every 5 to 8 years, with more frequent updates (see Timeliness) in areas of dynamic change (floodplains, landslides, large burn areas, developed areas). Have clarity in communications with partners about delivery dates. Any future lidar data is collected at QL1 (8 points per sq. m). Ideal goals: Entire state is covered by QL1 data, replacing areas of current QL2 data. Turnaround time is less than one year from acquisition to publication. Complete statewide point cloud classification, including buildings and vegetation. A pool of funding is available for Lidar updates, shortening the elapsed time from identifying a need for data, funding data acquisition, and acquiring the data. Core products – DSM, bare earth DEM, hydro-flattening, hydro-enforcement, certified contours, fully classified point cloud, canopy height, hillshade – are available statewide, are created with consistent statewide methods, and are updated regularly as new data are acquired. DEMS are hydro-enforced and ready for elevation derived hydrography. Process (and plan) in place to generate a complete statewide coverage every 5 to 8 years, with more frequent updates in areas of dynamic change (floodplains, landslides, large burn areas, developed areas). LIST: A map of areas needing frequent lidar reacquisition is developed and may include, areas of rapid development, dynamic rivers, urgent projects, and change detection needs Any future lidar data is collected at QL1 (8 points per sq. m). Ideal goals: Entire state is covered by QL1 data, replacing areas of current QL2 data Turnaround time is less than one year from acquisition (publication or preliminary data). Assist state agencies in bringing lidar and products into their business workflows Complete statewide point cloud classification, including buildings and vegetation. Users are informed of variable accuracy. Data limitations are communicated. Core products – DSM, bare earth DEM, hydro-flattening, hydro-enforcement, certified contours, fully classified point cloud, canopy height, hillshade – are available statewide, are created with consistent statewide methods, and are updated regularly as new data are acquired. DEMS are hydro-enforced and ready for elevation derived hydrography.
Current and Near-term Goals: Narrative - Baseline statewide lidar collection is completed.USGS Lidar Base Specifications (adopted by the Montana Lidar Plan) are achieved statewide in 2026. A core-set of lidar-derived products are made available statewide, including bare-earth DEM, DSM, intensity, hillshade, and canopy height. DEMs are hydro-flattened. LIST: A core-set of lidar-derived products are made available statewide, including bare-earth DEM, DSM, intensity, hillshade, and canopy height. DEMs are hydro-flattened. Create a feature class of collection dates Determine if MSL should only dessiminate derived products and state-led projects, and/or projects that are not in the USGS National Map. State Lidar data are accepted and added to the USGS National Map. Decrease MSL level of effort on lidar data requests (make more available online). Provide educational materials to users on production processes. Have clarity in communications with partners about delivery dates. Add missing or new lidar projects and state DNRC UAV lidar projects to the Montana Lidar Inventory. Lidar web services are broadly available and stable for external use.
Measure | Outcome | Action | Ongoing Action (Y/N) | Progress Assessment (% - Date) | LOE (staff time) | LOE/Cost External Support | Infrastructure | Feasibility and Comments
select from list | <Describe desired outcome, headed by time frame: “Current”; “Near-term”; “Long-term”> | <Actions needed to achieve outcome> | <Is the action underway (Y/N); may note reoccuring> | <Date and progress toward outcome; may be updated> | <Can the action be accomplished at current staffing (y/n)? Provide an estimate of hours> | <Is external support needed (y/n)? Provide an estimate of hours or cost> | <Is the necessary infrastructure in place (y/n). Provide an estimate of cost> | <Note that future ideas, currently infeasible, can be listed>
Completeness | Near-term: Complete base statewide coverage for each of the five core products at 1 meter resolution. | Remaining areas are in progress through the USGS 3DEP, expected delivery is Spring 2026 with MSL processing summer 2026. | Yes | 90% - 1/21/26 | Yes 120 hours. | No | Yes MSL has planned for 300 TB of storage at State Data Center, with plans to transfer to cloud environment (Rok). | Will be achieved in 2026
Timeliness | Long-term: Users have access to metadata that describes the span of time (weeks or even days) over which a given area was collected in general and by project. Present, but not specific enough dates for some users since reports are to the month | Create a metadata capability, map, or feature class of collection dates (Currently have collection months and year). | Yes | 40% -1/1/2026 | Yes 240 hours. | No | Yes | Achievable atleast at project level. Statewide is unkown, but promising.
Archive Frequency | Near-term: Evaluate duplication of online and archival data by other agencies (USGS National Map, notably) | Determine if MSL should only store MT derived products and state-led project, and/or projects that are not in the USGS National Map. | No | 0% | Yes 120 hours. | No | Yes | Achievable, may lead to reduced staff loe (e.g, with requests) and storage savings
Integrity | Near-term: State Lidar data are accepted and added to the USGS National Map. | Continue work with DNRC and their contractors to complete corrections identified by USGS | Yes | 35% - 1/26/26 | No, not much MSL can do unless we have funding to provide. | Yes (see GIS Plan gap funding analysis) | Yes | Feasiblity is unclear because many of these project are over 5 years old. USGS has already begun recollecting. Contractors need to make the corrections and funding is needed.
Consistency | Long-term: Focus to date has been on ground elevations. A more complete point cloud classification statewide is desired, including classification of buildings, low/med/high vegetation. Work completed in Sanders County is an example. | Develop point cloud classification workflow in house or contract work | Yes | 3% - 1/21/26 | No, would need to develop expertise. | Yes $45 per square mile based on Sanders 2023 project. | No. Some storage cost considerations | May not be feasible due to cost. Users could potentially complete classification themselves as needed, although consistency statewide is preferred.
Update Frequency | Long-term: Archive 12-20% new per year to achieve ideal 5-8 year statewide refresh. | Continue to support lidar collection through the USGS 3DEP. | Yes | 15% - 1/28/2026 | Yes 100 hours. | Yes Heavily dependent on Federal funding support through the USGS 3DEP. | No. Storage growth, approx. 45 TB per year. | Without state funds, new lidar collections are heavily dependent on federal funding. Some partner funding may be available, but the bulk of funding will need to come from USGS 3DEP, FEMA, or NRCS.
Update Frequency | Near-term: Areas impacted by major landscape change events (e.g., flooding, landslides, earthquake, rapid development) are updated within a year of the event. | A map of areas needing frequent lidar reacquisition is developed and may include, areas of rapid development, dynamic rivers, urgent projects, and change detection needs. There may be areas that seldom need updates and a map of low frequency should also be developed in the short-term. Long-term Identify process/program that can respond rapidly to change events | No | 0% | Yes 80 hours. | Yes A program that can respond rapidly to a change event and fund a lidar acquisition is unknown | Yes Storage growth. Unknown TB. | Heavily dependent on federal dollars, perhaps USGS or FEMA. Emergency response.
Archive Frequency | Near-term: User can retrieve a version of any project dataset (not necessarily authoritative) as it existed for the month and year collected | Continue current approach to archiving (annual). Original collections are available as projects (county). | Yes | 90% - 3/13/2026 | Yes 10 hours. | No | Yes Have planned for 300 TB of storage at State Data Center. | Will be achieved in 2026.
Archive Frequency | Near-term: The Library has a storage system capable of retaining and serving both project data (as presently done) and statewide (seamless) elevation products in the near future | Determine efficient storage and retrieval methods, estimating storage needs as part of determination, then put in place sufficient, expandable storage | Yes | 10% -1/28/2026 | Yes 1000 Hours?? | Yes Rok cloud implementation needed. | No, not currently, but should be covered by Rok implementaiton | Achievable, Rok cloud move will help
Archive Frequency | Near-term: Users can retrieve products and projects from a single portal, regardless of where these are hosted | Investigate ways to pass data queries through to other sources | No | 0% | Yes 200 hours. | No | Yes | Achievable, may lead to staff time (e.g, with requests) and storage savings.
Precision/Accuracy | Near-term: Entire state is at QL2 collection | Current Lidar Plan is executed | Yes | 90% - 3/13/2026 | Yes 0 hours (awaiting USGS) | No (in place, awaiting USGS) | Yes | Achievable, nearly complete.
Precision/Accuracy | Long-term: Entire state is at QL1 collection level | Update State Lidar Plan to require QL1 (currently recommended) | No | 0% | Yes 2 hours. | No | No. Storage would grow dramatically. | Significant cost considerations (acquisition and storage) that may hinder feasibility
Precision/Accuracy | Near-term: Users are informed of variable accuracy across each project (common due to technical limitations) | Make gridded spatial accuracy products (provided with some projects) and similar products available without need to make specific request of MSL staff | No | 0% | Yes 120 hours? | Yes May need expertise/consulting assistance. | Yes | Ability to accomplish task statewide is unknown but is likely achievable for some projects.
Integrity | Near-term: Users understand appropriate use of contours. 1-foot contours are pushing limits. In general assume +/- 1 foot. | Responses to lidar requests for contours state, "for preliminary planning only." Contours are largely for visual purposes. Also add documentation to web. | Yes | 50% - 1/25/26 | Yes 4 hours. | No | Yes | Achievable, underway. Add documentation to web.
Integrity | Near-term: USGS quality control processes and data review are applied to all collections. | Ensure that project partners (e.g., DNRC) include USGS quality control processes as specifications when conducting data collection and inspection. | No | 0% | Yes 40 hours. | Yes DNRC would need to be onboard. USGS would need to provide expertise and review. | Yes | Improvments can be made, but review may not be as robust as USGS QC process.
Precision/Accuracy | Long-term: 1/2 meter DEM resolution statewide (consistent with QL1 goal) | Future collections identify 1/2 meter DEM as deliverable. | Yes | 20% | Yes increased processing time. | Yes Additional funding is needed for higher quality level collections. | No. Storage would grow dramatically. | Feasible longterm only if federal funding is available through USGS 3DEP or FEMA.
Precision/Accuracy | Near-term: Avoid duplicative control point collection, which adds to cost and delay in data collection | Evaluate and make available control points collected as part of lidar acquisitions | No | 0% | Yes | Yes Would benefit from contractor expertise. | Yes | It is unclear how existing control may be used by lidar contractors
Consistency | Current: USGS QL2 base specification is used (or exceeded) in all new data collects | Ensure that project partners (e.g., DNRC) include USGS QL2 base specification | Yes | 90% - 3/13/26 | Yes | No project partners would need to and be willing to adopt specification | Yes | Already implemented by state agencies; new lidar is collected at QL2 or better whenever feasible
Consistency | Near-term: When projects are proposed or planned along state borders, states collaborate when possible | Identify communication methods and key contacts in adjacent states | Yes | 75% - 3/13/2026 | Yes | No, although adjacent states need to be engaged | Yes | NOAA U.S. Interagency projects in progress and completed: https://coast.noaa.gov/inventory/ Elevation Inventory: https://www.usgs.gov/media/images/usiei-us-interagency-elevation-inventory-interface
Completeness | Near-term: Tribal areas are available per data sovereignty guidance from Tribal Nations | Consultation with Tribal Nations | No | 20% - 3/13/2026 | Yes | Yes, Tribal contacts and engagement is needed | Yes | In process, USGS has asked State to work with Tribal Nations. Tribal Nations have been directing uses to MSL, though we cannot provide the data.
Consistency | Near-term: Limitations of Digital Surface Models are communicated | Document DSM creation process and inconsistencies that may be caused by limited point cloud classification | Yes | 50% - 3/13/2026 | Yes | No, although outside consultation may be helpful | Yes | Montana Lidar Inventory documentation has been improved. Lidar processing 101 workshop has been developed.
Consistency | Long-term: future lidar deliverables include hydro-enforcement | Update specifications and desired/required deliverables in the Montana Lidar Plan and/or Hydrography Plan. Assess cost. | No | 0% | Yes | Yes, hydro-enforcement would increase costs (contractors needed0 | No, increased storage | MSL can recommend specs and deliverables for future lidar. MSL does not currently have the inhouse skills to complete hydro-enforcement (could learn).
Consistency | Long-term: lidar-derived contours are certified (e.g., following FEMA requirements) | Determine what makes contours “certified” and then plan how to generate certified contours. | No | 10% - 3/13/2026 | Yes, maybe (unsure) | Yes, support from contractors needed | No, increased storage costs. | For example, see https://www.fema.gov/sites/default/files/documents/fema_MT-1-technical-guidance_112021.pdf Contours are a popular request. MSL can generate contours for visual purpose only; they are not certified contours. QL2 lidar may not be appropriate for 1-foot contours (as a general rule +/- 1-foot, especially in vegetated areas)
Consistency | Long-term: Hydrography products are updated with new lidar acquisitions, so that the two datasets are consistent | Plan for, then create, workflows that start hydrography updates when new lidar data pass quality control | No | 0% | No | Yes, USGS support. Funding support. | No, costs | Financially not feasible. Heavily reliant on federal funding. The main issue is hydrography will be created from old lidar (the two need to be better synced).
Timeliness | Current: Proposed and upcoming acquisitions are announced and can be readily looked up. | Post on MSDI Elevation web, Montana Lidar Inventory, and also send notices using MSL GovDelivery | Yes | 85% - 3/13/2026 | Yes | No | Yes | mechanisms are in place, frequency of updates could be improved; USGS delivery dates are a best guess (often off by many months)
Timeliness | Near-term: Areas that will be collected are planned in advanced to cover entire state every 5 to 10 years. | Develop ideal lidar Areas of Interest (5 to 10) for dividing up the state. Work with lidar vendors to identify ideal flights | Yes | 5% - 3/13/2026 | Yes | No, contractor input would help | Yes | This would develop a statewide plan for continued lidar acquisition, which will be nice to have…however, lidar acquisitions have chased opportunity and flexibility is needed when/where funding is available. The plan may also be driven by the age of existing lidar.
Timeliness | Near-term: triggers that should provoke new lidar collections are identified and publicized in advance (e.g., new road construction, landslide, major fire). | Develop triggers and share them with major agencies and others, so that new lidar collection can be performed | No | 0% | Yes | No, although partner interest and engagement is necessary | Yes | aspirational to have; however, success would depend on having funding to collect lidar shortly after events.
Timeliness | Near-term: Areas of concern (frequent change), such as floodplains, are identified | Develop map(s) of areas where frequent topography change is expected (such as floodplains, mining, high-development) | No | 0% | Yes | No, although input from other partners and contractors would help | Yes | aspirational to have; however, success would depend on having funding to collect lidar shortly after events.
Timeliness | Long-term: Lidar acquisition is aligned with local, state, federal projects and plans so that lidar is available at beginning of project or planning effort. | Gather plans from federal and state agencies that might benefit from lidar baseline, coordinate with agencies to help them include lidar in the action | No | 0% | Yes | No, although partners would need to be active participants | Yes | important for long-range State and Federal planning
Timeliness | Near-term: Preliminary data is delivered from vendor within 1 year of acquisition | Include preliminary data delivery within contract scopes | Yes | 10% - 1/15/2026 | Yes | Yes, USGS needs to be able to include preliminary data as a deliverable for all projects within MT | Yes | Preliminary data should not be shared with non-partners, greatly limiting the benefit of preliminary data (even when risks are known and clearly communicated).
Timeliness | Long-term: Final data are delivered within 1 year of acquisition | Work with USGS to determine how best to minimize bottlenecks; advocate for more resources if needed | No | 15% - 3/13/2026 (NSGIC has advocated in past) | No | Yes, USGS | Yes | Dependent on USGS; not much MSL can do other than advocate
Integrity | Near-term: Users can get to documentation on how data are collected and processed | Gather documentation from vendors and primary data processors; create and maintain MSL documentation on data processing; make available to users by posting within inventory and including it when users download or are sent data | Yes | 80% - 3/13/2025 | Yes | No | Yes | documentation has been improved. MSL processing doc could be made ready for public. Lidar processing 101 workshop (MARLS) could be added to web. Create or provide links to videos and other materials that describe how data are collected, processed, and might best be used
Integrity | Near-term: User understands that archive on given day may not match reality (e.g., mismatch between elevation and ground, orthomagery and hydrography) | Provide educational materials to users on production processes | No | 0% | Yes | No | Yes | better documentation of lidar accuracy statewide is needs, as it can vary by project. Users need to understand lidar has a better horizontal accuracy than imagery. If hydro aligns with elevaiton, it may not align with imagery--which can be confusing as users typically think of imagery as the measure of reality.
Relevance | Near-term: The value of current data offerings (the five core products) is assessed, and improvements or changes can be planned based on these | As users obtain lidar data and products, ask them to provide feedback on the products. Regularly review submitted information and summarize in a report. | Yes | 95% - 3/13/2026 (continuous, ongoing) | Yes | No | Yes | This is current practice
Relevance | Users understand appropriate use of lidar-derived contours | Appropriate use of contours is documented and provided with any request (e.g, "for visual use only"). | Yes | 70% - 3/13/2026 | Yes | No, although outside consultation may be helpful | Yes | staff have been instructed to include "for visual purposes only" with all lidar requests. More online documentation, knowledge base is needed.
Relevance | Near-term: People unfamiliar with lidar have resources to discover what it is and how it is used | Create or provide links to videos and other materials that describe how data are collected, processed, and/or might best be used | Yes | 70% - 3 | Yes | No | Yes | MSL lidar program has focused much on reaching the beginner. Lidar posters, postcards, stickers and other swag have been instrumental and should continue.
Relevance | Long-term: State programs, statutes, and business workflow that could or should use lidar and derived products as information sources incorporate them into their activities (e.g., monitoring land disturbance and reclamation, water models) | Assist appropriate state agencies in bringing lidar and products into their workflows (what are the current hurdles). This involves understanding their needs and assessing if (and then how) lidar and products can be used. May also involve determining whether products need to be altered to fit common needs. One useful approach – used with hydrography some years ago – is to examine each statute or program and how it might use lidar and elevation-derived products. | No | 0% | Yes | No, although agency input and participation would be needed | Yes | initially, largely a research exercise
Relevance | Near-term: Lidar web services are broadly available and stable for external use (lidar web service are currently made available through ArcGIS Online but intended for use through public MSL applications only. They are currently not intend for broad use or use in external agency applications) | Make lidar services public | No | 0% | Yes | No (assumes Rok cloud environment) | No, may be soon | Shoud be feasible with new cloud environment
Relevance | Near-term: Increase use by making data more readily available online (reduce "by request only"). LOE by MSL is lessened, thanks to more key products becoming help yourself (available online). | Near-term: Use the lidar use survey and data request survey to assess how best to make the point cloud (and other common products) available by download through MSL or USGS but not both. | No | 0% | Yes | No | Yes | currently at full capacity with lidar requests (March 2026).
Relevance | Long-term: CAD users can readily take advantage of lidar at MSL. | Identify and provide lidar products that are ready for CAD users. | Yes | 50% - 3/13/2026 | Yes | No | Yes | Surveryors and engineers are big user communities for lidar, but they generally don't have GIS software. How can MSL reduce hurdles and better meet their needs? Currently, MSL completes limited custom requests.
Completeness | short-term: The Montana Lidar Inventory is the state repository for all lidar collections | Add missing lidar projects and state DNRC UAV lidar projects. | Yes | 95% - 10/15/2026 | Yes | No | Yes
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list

## Value List
Measure | Definition
select from list
Update Frequency | Update Frequency: This is an aspect of "Timeliness", specified in this assessment because it is usually an explicit part of data management workflows
Archive Frequency | Archive Frequency: This is an aspect of "Timeliness", specified in this assessment because it is usually an explicit part of data management workflows
Precision/Accuracy | Precision/Accuracy: A measure of the accuracy of the data. Is the accuracy stated? Does it match end user’s needs?
Consistency | Consistency: A measure of the similarities and differences between data stored in multiple datasets or databases.
Completeness | Completeness: A measure of how comprehensive the information in a dataset is. Are required or priority fields populated?
Timeliness | Timeliness: An assessment of the data’s update cycles, and temporality to internal and external deadlines and reporting needs.
Integrity | Integrity: An assessment of whether the data’s structure, schema and maintenance workflows meet end user’s needs and support interopability between systems
Relevance | Relevance: An assessment of the accessibility and availability of data required to inform business systems and answer business questions.
Ongoing Action
Yes
No