## Sheet1
MSDI Data Improvement Plan
Theme: Hydrography AND Hydrologic Units
Represents the watercourses of Montana, including rivers, streams, lakes, ponds, canals, springs, watershed boundaries, and more.
Summary Five year goals: Ensure hydrography and elevation (lidar) planning, acquisition, and delivery are coordinated; Focus on business relevance; Update (or advocate for) watershed boundaries that are based on lidar-derived elevation; Make derivatives of the elevation-derived hydrography process, such as culverts, flow direction, and flow accumulation, available for additional purposes; Document how 3DHP and the National Wetland Inventory complement one another.
Summary Near-term goals - Consolidate MSDI Hydrography and MSDI Hydrologic Units; Develop a general strategy for statewide 3DHP data acquisition, including map(s) of collection areas, timelines, and cost estimates; Focus on business relevance; Provide webinar training and/or workshops about 3DHP, with an emphasis on Montana; Apply annually to USGS 3DHP DCA - Focus on finding partners and funding
Measure | Outcome | Action | Ongoing Action (Y/N) | Progress Assessment (Date) | LOE (staff time) | LOE/Cost External Support | Infrastructure Cost | Feasibility and Comments
select from list | <Describe desired outcome, headed by time frame: “Current”; “Near-term”; “Long-term”> | <Actions needed to achieve outcome> | <Is the action underway (Y/N)> | <Date and progress toward outcome; may be updated> | <Can the action be accomplished at current staffing (y/n)? Provide an estimate of hours> | <Is external support needed (y/n)? Provide an estimate of hours or cost> | <Is the necessary infrastructure in place (y/n). Provide an estimate of cost.> | <Note that future ideas, currently infeasible, can be listed>
Update Frequency | Current - No updates. Necessary updates will have to happen on an ad hoc basis, be stored and maintained locally, and may be replaced when 3DHP is complete. | Focus effort on planning, coordination, and, transitioning to the USGS 3DHP. | Yes | ongoing, continuous | Yes | Yes, USGS and federal funding necessary | Yes | dependent on USGS and funding levels; Feasible but the timeframe is unknown.
Update Frequency | Long-term needs - Statewide update every 5-8 years, in sync with Elevation (lidar). More frequent (2-5 years) in flood-prone areas and as soon as possible after events. Update hydrography as soon as possible after lidar is acquired, or within 2-5 years. | Collaborate with the USGS 3DHP on update strategy | Yes | 5% -3-13-2026 | Yes, 520 hours | Yes, USGS and federal funding necessary | Yes (although there are unknowns re storage) | dependent on USGS and funding levels; Feasible but the timeframe is unknown.
Relevance | Near-term: MSDI Hydrologic Units and MSDI Hydrography become one Theme. | Seek MGIA Council approval to consolidate hydro and hydrological units | No | 0% | Yes | No | Yes | Council's decision
Update Frequency | Long-term needs - Hydrological Units are completed as part of 3DHP | Seek clarification from the USGS regarding timeline. 3DHP will include catchments, but it is unclear how/if these translate to new "WBD" | No | 10% | Yes | No | Yes | Are new watershed boundaries part of 3DHP?
Completeness | Near-term: Thorough understanding of 3DHP features as compared to NHD. How will density change? How many more features, and length? | review crosswalk of NHD to 3DHP to make sure water features needed by Montana partners continue to be captured | No | 5% - 3/13/2026 | Yes, 80 hours | Yes, input from USGS, input from local and state partners | Yes | This is a challenging task until 3DHP starts to become available in Montana. Actions are needed to prepare for 3DHP; what data will the state and other partners need to manage?
Archive Frequency | Current: No changes. The final NHD snapshot will remain in archive. | No action, status quo | No | 0% | Yes | No | Yes
Archive Frequency | Long-term: Annual where changes have been made to the dataset, with a straighfoward means for seeing the changes. Ideal archive would be time-enabled and document river channel movement and increasing/decreasing waterbodies (e.g, have an accurate channel centerline depiction for every 5-8 years and more frequent in some areas and after flooding events) | Create data snapshot when changes have been made. USGS intends to provide downloadable annually, so annual snapshot may suffice. | No | 0% | Yes (unkown LOE) | No | No, unknown storage costs
Archive Frequency | Long-term: Archiving of watershed boundary dataset may be infrequent, as changes often reflect improvement in accuracy, not true changes on the ground. | No action, status quo. The current practice of an annual archive is sufficient. | No | 0% | Yes | No | Yes
Completeness | Long-term: Larger scale watershed boundaries are available. | Use 3DHP catchments to generate HU14 digit level and HU16 digit level watersheds. | No | 0% | Yes (unkown LOE) | Yes, USGS (3DHP catchments are needed) | Yes
Precision/Accuracy | Near-term: NHD geometry is transferred into the 3DHP model. The spatial accuracy will reflect the NHD until the 3DHP is developed. | No action (USGS task) | Yes | 100% (USGS) | No | Yes (USGS) | Yes
Precision/Accuracy | Long-term: Compared to current Hydro, 3DHP is expected to greatly improve positional accuracy. While horizontal accuracy is not explicitly stated in 3DHP, features will be derived from best source lidar which has a horizonal accuracy averaging 8 inches and vertical accuracy averaging 4-8 inches. Elevations will be assigned to flowlines and waterbodies and will be accurate to within atleast 1 foot. | Assess accuracy as 3DHP data start to become available | No | 0% | Yes | Yes (USGS) | Yes | will be able to start assessing once 3DHP become available in MT
Consistency | Near-term: For atleast the next 5-8 years, Hydro will be a mix of NHD features and new 3DHP features. What are the impacts of this transition period on users? | Work with partners to understand impacts | No | 0% | Yes | No | Yes
Consistency | Long-term: Shift from heads-up digitizing with aerial imagery and other sources to geoprocessing on high-quality elevation (lidar) models to map surface water flow networks. Statewide features will be derived at the same-scale using the same USGS 3DHP specifications; thereby, greatly increasing statewide consistency compared to current practices. | Collaborate with the USGS 3DHP; identify funding partners; apply for DCA | Yes | 5% - 03/13/2026 | Yes | Yes (USGS) | Yes
Completeness | Transitioning to 3DHP. Users will have to rely on a static version of the NHD for multiple years while the 3DHP is developed. To date, other than experimentation and testing, no elevation-derived hydrography has been generated in Montana (a few areas are in progress). | Identify the impact of a static NHD while 3DHP is being identified. Is an interim dataset needed? | Yes | 10% - 01/16/2026 | Yes | No | Yes
Completeness | Culverts have not been mapped as part of the NHD but will be mapped during 3DHP...should they become a feature of MSDI Hydrography or a bi-product? | Determine if culverts and other features mapped as part of 3DHP should become part of MSDI Hydrography or how they will be maintained and distributed (statewide culvert database?) | Yes | 10% - 03/03/2026 | Yes | No (USGS advising) | Yes
Completeness | Near-term: 3DHP will be a complete statewide dataset; however, there may be additional features/attributes managed by Montana that need to be developed and maintained. | Identify features/attributes that will need to be maintained by Montana. | Yes | 10% - 3/13/2026 | Yes | No | Yes
Completeness | Near-term: A general plan or strategy is in place for building out 3DHP for Montana | Develop statewide project plan and/or a map and timelines to address needs/priorities. Describe 3DHP collection areas by Phase (year), and include cost estimates. Accomodate the need to be flexible and opportunistic with partners and funding. | Yes | 80% - 3/17/2026 | Yes | No | No
Completeness | Long-term goal: 3DHP development addresses mapping of new/matching Wetland data…or Hydro and Wetrip compliment one another, and represent comprehensive Surface Water Mapping | Evaluate how 3DHP and NWI Wetlands will work together. Will new NWI and 3DHP align? | Yes | 10% - 3/3/2026 | Yes | Yes (USGS and NWI/Wetrip leads) | No
Integrity | Long-term: Nationwide standards are maintained by USGS 3DHP: Elevation-derived Hydrography Specification and 3D Hydrography Program Specifications | Adopt 3DHP Specs for MSDI Hydro. Seek Council approval | Yes | 20% - 3/13/2026 | Yes | No | Yes | Council's decision
Timeliness | Long-term: Update cycle depends on MSDI Elevation (lidar). Ad hoc edits can be suggested through the USGS Markup Tool (tbd) | Identify steps that can be taken to align the timing of Elevation and Hydro development | No | 0% | Yes | Yes (USGS and significant funding) | No, unknown storage costs
Relevance | Long-term: Watersheds in Montana are important for water quality assessment and classification, reporting to the Environmental Protection Agency, water resources management, and as reference data for flood-risk modeling/mapping. Catchments provide a means for organizing water-related data. Focus on Internet of Water and geoconnex. | Document/refresh Hydro Uses Document | Yes | 70% - 02/10/2026 | Yes | No | Yes
Update Frequency | Long-term: Hydrography products are updated when new lidar acquisitions are completed, so that the two datasets are consistent and in-sync (same vintage) | Plan for, then create, workflows that start hydrograpy updates when new lidar data pass quality control | No | 0% | No | Yes, USGS | No | dependent on USGS and funding levels; does not currently seem feasible
Consistency | Long-term: Names in MSDI Hydrography are suitable for state and local needs (include more than GNIS) | Incorporate alternative and local names into MSDI Hydrography | No | 0% | No (unsure of effort) | Yes, USGS | Yes
Relevance | Long-term: Hydrography features are assigned a streamflow classificaiton (Intermittent, Perennial, Ephmeral) | Develop method to translate 3DHP flow probabilities into classification. | No | 0% | No | Yes, state partners and other users | Yes
Relevance | Near-term to long-term (ongoing): Hydro-enforced DEMs are available for additional analysis and purposes. Flow accumulation and flow direction rasters are also considered. | Work with the USGS and contractors to ensure hydro-enforced DEMs are included as a deliverable | No | 0% | Yes | Yes, (USGS support, contract adjustments) | No, storage considerations
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
select from list
Note on A4: Blandford, Troy:

## Value List
Measure | Definition
select from list
Update Frequency | Update Frequency: This is an aspect of "Timeliness", specified in this assessment because it is usually an explicit part of data management workflows
Archive Frequency | Archive Frequency: This is an aspect of "Timeliness", specified in this assessment because it is usually an explicit part of data management workflows
Precision/Accuracy | Precision/Accuracy: A measure of the accuracy of the data. Is the accuracy stated? Does it match end user’s needs?
Consistency | Consistency: A measure of the similarities and differences between data stored in multiple datasets or databases.
Completeness | Completeness: A measure of how comprehensive the information in a dataset is. Are required or priority fields populated?
Timeliness | Timeliness: An assessment of the data’s update cycles, and temporality to internal and external deadlines and reporting needs.
Integrity | Integrity: An assessment of whether the data’s structure, schema and maintenance workflows meet end user’s needs and support interopability between systems
Relevance | Relevance: An assessment of the accessibility and availability of data required to inform business systems and answer business questions.